## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
S1 | S1 | US-001 | Understand and document functional requirements for the AI-driven project intelligence and risk management platform | MUST HAVE | - | Mobashir Ashraf | 3- Completed
S1 | S1 | US-002 | Identify and collect a project-related dataset containing categorical and numerical features | MUST HAVE | US-001 | Mobashir Ashraf | 3- Completed
S1 | S1 | US-003 | Perform initial data inspection to understand dataset structure, feature types and value ranges | MUST HAVE | US-002 | Mobashir Ashraf | 3- Completed
S1 | S1 | US-004 | Perform data cleaning to remove duplicate and inconsistent records from the dataset | MUST HAVE | US-003 | Mobashir Ashraf | 3- Completed
S1 | S1 | US-005 | Handle missing values across categorical and numerical features | MUST HAVE | US-004 | Mobashir Ashraf | 3- Completed
S1 | S1 | US-006 | Perform initial exploratory data analysis (EDA) to understand feature trends and relationships | SHOULD HAVE | US-005 | Mobashir Ashraf | 3- Completed
S2 | S2 | US-007 | Process categorical features using appropriate encoding techniques | MUST HAVE | US-006 | Mobashir Ashraf | 3- Completed
S2 | S2 | US-008 | Process numerical features using scaling/normalization techniques | MUST HAVE | US-006 | Mobashir Ashraf | 3- Completed
S2 | S2 | US-009 | Perform feature engineering to prepare model-ready project risk indicators | SHOULD HAVE | US-007, US-008 | Mobashir Ashraf | 3- Completed
S2 | S2 | US-010 | Prepare training and testing datasets for model development | MUST HAVE | US-009 | Mobashir Ashraf | 3- Completed
S2 | S2 | US-011 | Train CatBoost and XGBoost models to predict project risk | MUST HAVE | US-010 | Mobashir Ashraf | 3- Completed
S2 | S2 | US-012 | Evaluate model performance using appropriate classification metrics | MUST HAVE | US-011 | Mobashir Ashraf | 3- Completed
S2 | S2 | US-013 | Select the suitable CatBoost and XGBoost models configuration based on evaluation results | SHOULD HAVE | US-012 | Mobashir Ashraf | 3- Completed
S3 | S3 | US-014 | Develop the FastAPI backend service structure for the platform | MUST HAVE | US-013 | Mobashir Ashraf | 3- Completed
S3 | S3 | US-015 | Create a prediction API endpoint to serve project risk predictions | MUST HAVE | US-014 | Mobashir Ashraf | 3- Completed
S3 | S3 | US-016 | Connect the trained CatBoost and XGBoost models with the FastAPI backend | MUST HAVE | US-015 | Mobashir Ashraf | 3- Completed
S3 | S3 | US-017 | Develop the Streamlit frontend application structure | MUST HAVE | US-013 | Mobashir Ashraf | 3- Completed
S3 | S3 | US-018 | Create a project risk dashboard interface in Streamlit | MUST HAVE | US-017 | Mobashir Ashraf | 3- Completed
S3 | S3 | US-019 | Integrate the Streamlit frontend with the FastAPI backend | MUST HAVE | US-016, US-018 | Mobashir Ashraf | 3- Completed
S4 | S4 | US-020 | Add risk analysis and project intelligence features to the dashboard | SHOULD HAVE | US-019 | Mobashir Ashraf | 3- Completed
S4 | S4 | US-021 | Integrate model prediction results into dashboard visualizations | MUST HAVE | US-020 | Mobashir Ashraf | 3- Completed
S4 | S4 | US-022 | Perform unit testing of individual application modules | MUST HAVE | US-019 | Mobashir Ashraf | 3- Completed
S4 | S4 | US-023 | Perform integration testing across the ML pipeline, API and UI | MUST HAVE | US-022 | Mobashir Ashraf | 3- Completed
S4 | S4 | US-024 | Fix issues identified during unit and integration testing | MUST HAVE | US-023 | Mobashir Ashraf | 3- Completed
S4 | S4 | US-025 | Finalize project documentation for internship submission | MUST HAVE | US-024 | Mobashir Ashraf | 3- Completed
S4 | S4 | US-026 | Prepare the application for demonstration and GitHub upload | COULD HAVE | US-025 | Mobashir Ashraf | 3- Completed
Note on F1: Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
Note on D2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on E2: Please enter the dates in either of these formats: 9/15/2016 or 15-Sep-2016
Note on I3: This is the total task estimated in hours for all the user stories
Note on J3: Pending effort hours after completion of day 1 work
Note on K3: Pending effort hours after completion of day 2 work
Note on L3: Pending effort hours after completion of day 3 work
Note on M3: Pending effort hours after completion of day 4 work
Note on N3: Pending effort hours after completion of day 5 work
Note on O3: Pending effort hours after completion of day 6 work
Note on P3: Pending effort hours after completion of day 7 work
Note on Q3: Pending effort hours after completion of day 8 work
Note on R3: Pending effort hours after completion of day 9 work
Note on S3: Pending effort hours after completion of day 10 work
Note on T3: Pending effort hours after completion of day 11 work
Note on U3: Pending effort hours after completion of day 12 work
Note on V3: Pending effort hours after completion of day 13 work
Note on W3: Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1
2
3
4
5
6
7